No	Ref	Subject	Action Required	Owner	Meeting Date	Date Due	Progress / Comment	Date / Completed	Status
1	CM/11/24/52	Response to Ofsted Inquest – Protecting CQC colleague and Provider Welfare - Learning Resources	The paper was due to be presented to the Board in November 2024 but was deferred for consideration at the March meeting.	Chris Dzikiti	27/11/24	26/03/25	To be considered at the March 2025 meeting
2	CM/09/24/23	Strategic and Policy Approach Towards an Anti-Racist Approach in CQC	JF to clarify the Board’s role in implementing change.	Joyce Frederick	25/09/24	26/03/25	For consideration at the March 2025 Board meeting
3	CM/09/24/24	WRES & WDES Report and Action Plan	JJ and NR to conduct a detailed examination of policies and procedures, outlining actions necessary to bring about significant change in Equality, Diversity, and Inclusion.	Jackie Jackson	25/09/24	26/03/25	For consideration at the March 2025 Board meeting
4	CM/09/24/41	National maternity inspection end of programme report and supporting improvement resource	CD to evaluate in 12 months, whether this initiative has led to any positive outcomes.	Chris Day	25/09/24	24/09/25	Further information will be provided at the September 2025 meeting
5	CM/11/24/21	Key points on Recovery	James Bullion/The Chief Executive to report on impact of the new approach on the numbers of assessments conducted across health and social care.	Julian Hartley	27/11/24	05/02/25	Further information will be provided at the meeting
6	CM/11/24/22	Report from the Executive Team	JB to report on impact of ICETR on people’s quality of life.	James Bullion	27/11/24	26/03/25	Further information will be provided at the March meeting
7	CM/11/24/23	Management response to Penny Dash & Mike Richards Report	The Chief Executive should report further publication of reports to the Board alongside the timeline for completion of recommendations.	Julian Hartley	27/11/24	5/02/25	Further information will be provided at the meeting
8	CM/11/24/24	Corporate Performance Report (Q2 and September 2024)	Sean Cornall to review out of hours inspections and provide information to the Board.	Sean Cornall	27/11/24	5/02/25	The Deputy Director of Performance is writing a paper for Reg Governance Committee on this currently and will provide an update via the cover paper at Board when performance is next on the agenda.	28/01/25
9	CM/11/24/24	Corporate Performance Report (Q2 and September 2024)	Sean Cornall to adapt the Performance reporting to reflect recovery priorities by sorting high-priority items into the top right quadrant and emphasising them at the top of the scorecard for better visibility.	Sean Cornall	27/11/24	05/02/25	We will review this reporting suite, using the recovery priorities as defined by the Board.	28/01/25
10	CM/11/24/24	Corporate Performance Report (Q2 and September 2024)	Sean Cornall to work with Performance and Engagement colleagues to identify data sources to include user experience with the regulatory platform in the relevant reporting material.	Sean Cornall	27/11/24	26/03/25	Further information will be provided at the March meeting
11	CM/11/24/24	Corporate Performance Report (Q2 and September 2024)	CD to highlight successful instances of regulatory impact and make the positive outcomes more visible to help balance the feedback.	Chris Day	27/11/24	05/02/05	Further information will be provided at the meeting
12	CM/11/24/25	Quarterly People and Culture Assurance Report	JJ to establish KPI and track varying levels of staff wellbeing	Jackie Jackson	27/11/24	26/03/25	Further information will be provided at the March meeting
13	CM/11/24/25	Quarterly People and Culture Assurance Report	JJ to ensure that mandatory compliance courses were prioritised and relevant to teams. Progress update to be shared at the next Board meeting	Jackie Jackson	27/11/24	26/03/25	Further information will be provided at the March meeting
14	CM/11/24/25	Quarterly People and Culture Assurance Report	JJ to include in the 2025 business plan, metrics above the labour market benchmarks for workforce diversity and should be reflected in the Workforce Race Equality Standard Report and Workforce Disability Equality Standard Report.	Jackie Jackson	27/11/24	26/03/05	Further information will be provided at the March meeting

Status key:
- Red – overdue
- Geen - on track
- Blue – Complete or propose to close