## Slide 1: Priorities Programme – Foundational Improvements
Foundational Improvements
Operations and Regulatory Leadership Integration
Assessment Framework
Systems (including Regulatory Platform)
Organisational Data, Ratings and Register
Dr Penny Dash Report
Sir Mike Richards report
Colleague Feedback
Sector Feedback
Care Provider Alliance Report
Our Values and Purpose – internal launch over the Summer
Notes: 1

## Slide 2: Foundational Improvements
Operations and Regulatory Leadership Integration
Inspector and Assessor role reversion is complete. Between January and November, we have recruited 170 new Inspectors who have commenced employment with CQC.
Operations and Regulatory Leadership are now integrated under the Chief Inspectors from 3 November 2025.
Recruitment is underway for 6 sector-specific director role. The roles will be part of the Chief Inspectors Senior Leadership Team.
Recruitment to sector-specific deputy director vacancies will begin in November, with an aim to conclude by January 2026.
Assessment Framework
Chief Inspectors have been leading sector engagement events on the assessment framework and characteristics of ratings.
Consultation on improving how we assess, and rate providers is live – closing 11 December 2025.
We are hosting events in December 2025 for colleagues, providers and public representatives to look at the content of the assessment framework for the sectors, and the language and framing of the quality statements, alongside exploring what good quality health and care looks like.
Systems (including Regulatory Platform)
Extended legacy systems to ensure stability while new systems and processes are designed and then implemented
Registration has been moved off the regulatory platform and provider portal to ensure effective service available to providers.
Hybrid approach for assessment is used by all operational colleagues.
Organisational Data, Ratings and Register
Developing an approach to Co-design of a shared Data Strategy
Joint working with other stakeholders to implement 'Richards' recommendations regarding access to data.
Review of how data is organised and classified across CQC
Regulated Services Taxonomy: a new project has started to review and improve the taxonomy of our regulated services to bring consistency and coherence across our regulatory services (notifications, assessment, registration and enforcement).
Data platform development: new data modules have been incorporated into the Enterprise Data Platform (EDP) for notifications, market oversight and enforcement, meaning there is a single version of truth for these data sets. A platform improvement strategy has been developed.
Notes: 2

## Slide 3: Roadmap (phase 1) with indicative dates and stop points
Dec 26
July – Nov 26
Feb – Jun 26
Nov 25 – Jan 26
Oct 25
Oct 25
How we assess
Integration
Digital
Assessment rollout and ongoing development
Registration and enforcement technology and provider portal: Scoping
Assessment technology: Improving, testing and piloting internally and externally
Assessment rollout
Training and support
Feedback on consultation and sector frameworks; then pilots
Operations embed into new teams
Operations move into sector teams
Finalise system requirements
Publish new frameworks and consultation response
Develop and test guidance and training
Feedback on sector frameworks and pilots
Assessment framework and methodology: public consultation and testing
Agree approach to developing new assessment framework and methodology
Upgrading our systems for capturing, storing and analysing our data; embedding a data culture; and reviewing how we categorise data.
Assessment technology: Scoping, designing, and testing
Strengthening our digital infrastructure
Thinking through our future processes (registration, assessment, contact, enforcement)
Data
Notes: 4 workstreams
How the roadmap was developed
Dr Penny Dash, Professor Sir Mike Richards, and the Care Provider Alliance, alongside the independent review of our technology.
builds on our draft technology roadmap shared earlier this year
includes all aspects of how we will rebuild regulation and change how we work.
Road map was built by group directors and deputy directors
Brought insight from colleagues across all service lines, providers, the public and wider stakeholders to develop the plan collaboratively.
The roadmap
3 phases up to the end of 2028:
Phase 1 (now until end of 2026):
launch of the public consultation on our assessment framework.
Operational teams embedding new ways of working in their new structures, and continued work to support teams that are not yet in a new structure, for example regulatory coordinators and officers.
Continuing to review and implement smaller-scale improvements to our regulatory platform to help colleagues work more effectively, and to support health and wellbeing.
Responding to feedback on our assessment framework consultation, testing with colleagues and providers, and publishing the final framework.
A targeted consultation on sector-specific frameworks and what good health and care looks like.
Developing and piloting our new assessment technology (starting from spring 2026).
Creating training and guidance for colleagues and providers who need to use or access the assessment service, ready to start rollout of the assessment framework and technology (by the end of 2026 – if colleagues, providers and the public feel comfortable that we are ready).
Improving our digital capability and upgrading our data platform.
Engaging with key internal stakeholders to scope our future registration, assessment, enforcement and contact technology, and reflect on lessons learned, alongside scoping some improvements to the provider portal.
Reviewing the performance of our new assessment framework, technology and process, and making improvements.
Progress to first stop point in phase 1: For our first Stop point we have 9 key activities, and we have delivered 7 , with co-design and agreeing strategic outline case through governance needing a bit more work. They are:
a signed off assessment framework consultation document (already published)
an agreed approach to developing sector-specific assessment frameworks
a final operational team structure
an agreed co-design method for the changes
established robust governance for digital changes
a contract agreed to get more technology and data capacity
a ‘strategic business case’ in place for the plan (this is an overarching case for change, and will be followed by the ‘full business case’ later in the year)
approvals to move forward from the Investment Committee, the Department of Health and Social Care, the Executive Team and CQC’s Board.
Effective communications on the roadmap in place.
Phase 2 (end of 2026 to end of 2027): developing, testing and piloting our registration, enforcement and contact technology, along with an improved provider portal.
Phase 3 (end of 2027 to end of 2028): CI approach
Activity for phases 2 and 3 will be shared at a later date.
Phases and assurance
  Learning lessons from the past, we will pause, listen and check throughout each phase as we complete activities. This aims to provide assurance that we are ready to move forward. If more work is needed to make sure the change will be robust and effective, then more time will be agreed, with clear communication to support that.
Co-design and testing – doing things differently
  Co-design and testing will be essential to make sure that our new technology and ways of working meet the needs of colleagues and support their health and wellbeing, alongside the needs of providers and the public.
  Government Digital Service (GDS) standards will be followed to help us shape our technology in line with best practice, useability and accessibility.
  Learning from the past, an approach to how we co-design and test effectively will be shared soon, after discussions with the new colleague advisory group.

## Slide 4: CQC Way: Our values and purpose:
Employee
Lifecycle
Continuous Improvement
Leadership
External Stakeholders
Colleague Voice
Celebrating Success
Governance
The development of CQC Way was launched internally in July 2025 and externally from September 2025.
Throughout the colleague conferences in November 2025 the Executive team have set out seven priority areas for embedding work to be completed during the remainder of this financial year.
Notes: 10:43
Video