## Slide 1: Balanced score card CQC Business Plan 2025/26 Month 6 | September 2025 CM/11/25/42 Item 4.2 Performance, Finance and Risk Updates for Q2 – Appendix A

## Slide 2: Measure categories
Key
 | On or exceeding target
 | Nearing target
 | Off track
 | Management information only
 | Management information only but trend is unusual
 | Not reported in period
n/a | Not available
=< | ‘Equal or less’ than (all other targets are ‘equal or greater’ than unless otherwise specified)
Immediate Action Measures | Page 2, 3
Regulatory Effectiveness (Customer) | Page 4, 5
Business Processes | Page 6, 7
Finance | Page 8
Culture and People | Page 8

## Slide 3: Immediate Action Measures
 |  |  | 2025 |  |  |  |  |  |  |  |  | 2026 |  |  | 
Measure / Management Information | 25/26 Target | 24/25 Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Year to date
Total volume of assessments | 9,000 by Sep 2026 | 3,825 | 443 | 452 | 540 | 541 | 529 | 489 |  |  |  |  |  |  | 2,994
Total volume of assessments: Adult Social Care | 5,013 by Sep 2026 | 2,305 | 259 | 275 | 306 | 312 | 289 | 261 |  |  |  |  |  |  | 1,702
Total volume of assessments: Secondary Care | 887 by Sep 2026 | 230 | 22 | 33 | 39 | 20 | 46 | 33 |  |  |  |  |  |  | 193
Total volume of assessments: Primary Care and Community | 1,194 by Sep 2026 | 404 | 39 | 45 | 45 | 70 | 46 | 64 |  |  |  |  |  |  | 309
Total volume of assessments: Oral Health | 1,500 by Sep 2026 | 749 | 89 | 66 | 99 | 84 | 87 | 85 |  |  |  |  |  |  | 510
Total volume of assessments: Mental Health | 726 by Sep 2026 | 133 | 13 | 10 | 27 | 18 | 24 | 20 |  |  |  |  |  |  | 112
Time to complete assessments for Adult Social Care, Primary and Community Care, Oral Health and Health and Justice | =<50 days | 54 | 40 | 38 | 32 | 36 | 34 | 33 |  |  |  |  |  |  | 37
Time to complete assessments for Mental Health and Secondary Specialist Care | =<85 days | 116 | 159 | 109 | 74 | 57 | 74.5 | 49 |  |  |  |  |  |  | 83
% registration applications in the system over 10 weeks old and incomplete | 0% by end Q4 | 28.1% | 31.3% | 35.1% | 33.1% | 33.1% | 33.2% | 32.6% |  |  |  |  |  |  | 32.6%
The volume of registration applications over 10 weeks old and incomplete | 0 by end Q4 | 3,393 | 3,820 | 4,289 | 3,956 | 3,374 | 3,060 | 2,711 |  |  |  |  |  |  | 2,711
The volume of registration applications completed | Track for Info | 28,539 | 2,601 | 2,582 | 2,862 | 2,886 | 2,575 | 3,088 |  |  |  |  |  |  | 16,594
The % of registration applications that have been rejected | Track for Info | 38.1% | 34.0% | 29.7% | 26.9% | 25.9% | 37.7% | 36.5% |  |  |  |  |  |  | 32.6%
The volume of registration applications received | Track for Info | 68,966 | 5,123 | 5,409 | 5,631 | 6,038 | 5,576 | 6,337 |  |  |  |  |  |  | 34,114

## Slide 4
 |  |  | 2025 |  |  |  |  |  |  |  |  | 2026 |  |  | 
Measure / Management Information | 25/26 Target | 24/25 Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Year to date
% of 'Information of Concern (IOC) assigned initially as Priority 1 cases with a referral sent within 2 days | 95% | 92.1% | 92.1% | 96.7% | 96.6% | 89.0% | 89.8% | 88.1% |  |  |  |  |  |  | 92.1%
% of Information of Concern (IOC) Priority 1 cases with an action taken within 1 day of referral | 95% | 67.4% | 72.0% | 75.0% | 78.1% | 81.4% | 82.0% | 77.5% |  |  |  |  |  |  | 78.0%
% of Information of Concern (IOC) Priority 2 cases with an action taken within 10 days reducing to 5 days by year end | 95% | 78.5% | 84.6% | 85.8% | 89.0% | 86.1% | 87.6% | 88.5% |  |  |  |  |  |  | 86.9%
% of Information of Concern (IOC) Priority 3 cases with an action taken within 10 days reducing to 5 days by year end | 95% | 74.8% | 80.9% | 83.0% | 82.1% | 83.1% | 84.3% | 81.9% |  |  |  |  |  |  | 82.6%
Immediate Action Measures (continued)
Information of Concern cases are raised when information provided to NCSC raises safeguarding issues or other significant concerns for an individual regarding the health or care services they are receiving. These are then managed accordingly in line with the priority category they meet. Where relevant a referral is sent to the relevant Local Authority. These cases are risk reviewed by Operations teams and action is taken where necessary.

## Slide 5
 |  |  | 2025 |  |  |  |  |  |  |  |  | 2026 |  |  | 
Measure / Management Information | 25/26 Target | 24/25 Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Year to date
Age of assessments less than 5 years old | >69.6% | 69.6%* | - | - | - | - | 70.9% | 70.9% |  |  |  |  |  |  | 70.9%
Total quality statements assessed in completed assessments | Track for Info | 55,101 | 8,865 | 9,791 | 12,084 | 12,745 | 12,618 | 11,715 |  |  |  |  |  |  | 80,626
% Freedom of Information Requests (FOIs) answered to standard within 20 working days | 95% | 86.4% | 90.8% | 95.1% | 95.4% | 94.7% | 94.7% | 90.5% |  |  |  |  |  |  | 93.2%
% Subject Access Requests (SARs) answered to standard within statutory deadline | 95% | 84.6% | 85.3% | 86.1% | 91.5% | 95.2% | 97.2% | 97.1% |  |  |  |  |  |  | 91.5%
Maternity and Newborn Safety Investigations (MNSI) – To contact trusts within 2 days | 80% | 98% | 97% | 98% | 98% | 99% | 96% | 95% |  |  |  |  |  |  | 97%
Maternity and Newborn Safety Investigations (MNSI) – To contact families within 5 days​ | 80% | 100% | 100% | 98% | 100% | 98% | 100% | 100% |  |  |  |  |  |  | 99%
Maternity and Newborn Safety Investigations – Complete investigations within 6 months​ | 60% | 40% | 41% | 43% | 43% | 44% | 45% | 45% |  |  |  |  |  |  | 45%**
Maternity and Newborn Safety Investigations (MNSI) – Complete investigations within 6 months​ without exceptions / on holds | Sep 25: 60% Jan 26: 70% Mar 26: 80% | n/a (new) | 57% | 58% | 59% | 58% | 61% | 60% |  |  |  |  |  |  | 60%**
% of NCSC general enquiries line calls answered | 80% | 79.0% | 81.8% | 82.8% | 84.2% | 85.1% | 86.2% | 93.4% |  |  |  |  |  |  | 85.8%
% of NCSC registration line calls answered | 80% | 85.1% | 90.0% | 89.0% | 90.6% | 91.3% | 92.0% | 95.8% |  |  |  |  |  |  | 91.5%
% of NCSC mental health line calls answered | 90% | 81.4% | 95.6% | 89.5% | 93.1% | 94.1% | 95.0% | 94.6% |  |  |  |  |  |  | 93.7%
% of NCSC safeguarding line calls answered | 90% | 82.4% | 96.3% | 91.4% | 95.0% | 95.1% | 95.6% | 94.9% |  |  |  |  |  |  | 94.7%
Regulatory Effectiveness (Customer)
* This is the July 2025 baseline
** these year-to-date figures are the latest available 12-month rolling average.

## Slide 6
 |  |  | 2025 |  |  |  |  |  |  |  |  | 2026 |  |  | 
Measure / Management Information | 25/26 Target | 24/25 Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Year to date
Local Authority Assessments site visits (cumulative total reported each month) | 153 by Dec 2025 | 67 of 153 | 75 | 84 | 97 | 103 | 111 | 122 |  |  |  |  |  |  | 122
Local Authority Assessments reports published (cumulative total reported monthly) | 153 by Mar 2026 | 27 of 153 | n/a (purdah) | 40 | 45 | 53 | 63 | 70 |  |  |  |  |  |  | 70
Availability of CQC 'Business Critical' Systems | 99.80% | 99.98% | 99.97% | 100% | 99.90% | 100% | 99.97% | 100% |  |  |  |  |  |  | 99.99%
Customer satisfaction with CQC's website and give feedback on care service | 85% | 80% | 82.5% | 80.8% | 83.4% | 83.8% | 69.8%* | 63.3%* |  |  |  |  |  |  | 80.3%*
The number of health and safety incidents, accidents and near misses (incl. verbal/physical abuse) | Track for info | 192 | 14 | 10 | 20 | 32 | 12 | 25 |  |  |  |  |  |  | 113
Ionising Radiation Medical Exposure Regulations (IR(ME)R) regulatory activity volumes | 120 | 67 | Quarterly |  | 22 | Quarterly |  | 32 | Quarterly |  |  | Quarterly |  |  | 54
Multi-agency activity volumes (regulatory and non-regulatory): Children's team | 70 | 155 | Quarterly |  | 21** | Quarterly |  | 21** | Quarterly |  |  | Quarterly |  |  | 42**
Multi-agency activity volumes (regulatory and non-regulatory): Health & Justice team | 86 | 86 | Quarterly |  | 23** | Quarterly |  | 23** | Quarterly |  |  | Quarterly |  |  | 46**
Multi-agency activity volumes (non-regulatory): Safehouses team | 38 | 40 | Quarterly |  | 7** | Quarterly |  | 9** | Quarterly |  |  | Quarterly |  |  | 16**
Multi-agency activity volumes (non-regulatory): Defence team | 64 | 48 | Quarterly |  | 9** | Quarterly |  | 12** | Quarterly |  |  | Quarterly |  |  | 21**
Medicines Optimisation regulatory activity volumes | 800 | 707 | Quarterly |  | 180 | Quarterly |  | 262 | Quarterly |  |  | Quarterly |  |  | 442
Business Processes
* GFOC not included - system is currently unavailable. Potentially subject to change.
** Multi-agency assessments are currently meeting SLAs for each area. Assessments numbers are determined based on agency decisions on how best to use our resources. This could mean undertaking one very large assessment or several smaller ones.

## Slide 7
 |  |  | 2025 |  |  |  |  |  |  |  |  | 2026 |  |  | 
Measure / Management Information | 25/26 Target | 24/25 Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Year to date
% of Second Opinion Appointed Doctor (SOAD) appointed within timeframe* | 70% | 71% | 79% | 75% | 71% | 65% | 63%* | 57%* |  |  |  |  |  |  | 68%*
% Section 61 reports scrutinised within 14 days | 97% | 97% | 95% | 100% | 100% | 100% | 96% | 100% |  |  |  |  |  |  | 99%
The number of second opinions awaiting an appointment | <=1,391 | n/a (new) | 1,359 | 1,273 | 1,330 | 1,486 | 1,526 | 1,650 |  |  |  |  |  |  | 1,437**
The number of Mental Health Act Operations (MHAO) monitoring visits undertaken | >=62 visits per month | n/a (new) | 62 | 71 | 75 | 64 | 75 | 95 |  |  |  |  |  |  | 442
Number of Mental Health Act Operations (MHAO) Independent Care and Treatment reviews (ICETR) undertaken | 6 per month | n/a (new) | 5 | 3 | 5 | 7 | 4 | 4 |  |  |  |  |  |  | 28
Business Processes (Continued)
* SOAD data is lagged and cannot be produced until 1-2 months following the period. August/September are subject to minor change as 9 out of 2,076 requests are still within timeframe but are not yet appointed.
** This is the year-to-date average

## Slide 8: Culture and People
 |  |  | 2025 |  |  |  |  |  |  |  |  | 2026 |  |  | 
Measure / Management Information | 25/26 Target | 24/25 Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Year to date
% capital spend variance to budget | -1% to 1% variance | 7% | 1036.9% | 100.0% | -41.3% | 100.2% | 89.2% | -66.5% |  |  |  |  |  |  | 48.1%
% revenue spend variance to budget | -1% to 1% variance | 1.5% | 2.7% | -8.3% | 2.4% | 0.4% | -2.7% | 4.3% |  |  |  |  |  |  | 0.0%
Finance
 |  |  | 2025 |  |  |  |  |  |  |  |  | 2026 |  |  | 
Measure / Management Information | 25/26 Target | 24/25 Result | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Year to date
% of staff turnover | <10% | 8.0% | 8.0% | 8.2% | 7.9% | 8.0% | 8.0% | 7.6% |  |  |  |  |  |  | 7.6%*
% of staff vacancies | <5% | 8.1% | 8.1% | 7.8% | 7.5% | 7.1% | 6.6% | 6.9% |  |  |  |  |  |  | 6.9%*
% of staff sickness | <5% | 4.3% | 4.3% | 4.3% | 4.2% | 4.1% | 4.0% | 4.0% |  |  |  |  |  |  | 4.0%*
% of staff from an ethnic minority background | 17.9% | 17.6% | Quarterly |  | 18.4% | Quarterly |  | 17.6% | Quarterly |  |  | Quarterly |  |  | 17.6%*
% of staff with a disability | 18.4% | 15.1% | Quarterly |  | 15.4% | Quarterly |  | 15.4% | Quarterly |  |  | Quarterly |  |  | 15.4%*
% of stakeholders who have positive sentiment toward ‘I have a good understanding of CQC's regulatory approach' | 75% | n/a (new) | Annual |  |  |  |  |  |  |  |  |  |  |  | n/a
% of stakeholders who have positive sentiment towards ‘I believe the changes CQC is making will improve how it regulates' | 62% | n/a (new) | Annual |  |  |  |  |  |  |  |  |  |  |  | n/a
* these year-to-date figures are the latest available 12-month rolling average

## Slide 9: Corporate Risk
Reference | Risk | Risk Score | Appetite | Tolerance | Risk Status
Operations and Delivery |  |  |  |  | 
Op2a Achieving 9000 assessments by September 2026 | If we do not meet our assessments target of 9000 by September 2026, then we will be unable to improve our regulatory credibility | 10 | 8 | 12 | Exceed Appetite
Op2b. Improving longer term productivity | If we are unable to increase the number of assessments completed to compare with previous years prior to transitioning to our new ways of working, then we will be unable to drive improvement and improve our regulatory credibility | 25 | 8 | 12 | Exceeds Tolerance
Op3a. Stuck assessments | If we have assessments stuck in the system that cannot progress beyond different stages of the assessment process, then we will not be able to deliver of our core services. | 4 | 8 | 12 | Within Appetite
Op3b. Delays in publishing reports | If we experience delays in publishing reports due to operational resource to prevent, then we will not provide timely delivery of assessment services | 12 | 8 | 12 | Exceeds Appetite
Op4. Registration | If we are unable to process registrations within 10 weeks, then we will not meet our SLA target impacting the market and our credibility | 12 | 8 | 12 | Exceeds Appetite
Op5. Information of Concern | If we do not meet ongoing information of concern KPIs whilst delivering quality and a satisfactory customer experience, then this will impact our ability to accurately identify and respond to regulatory risk | 12 | 8 | 12 | Exceeds Appetite
Op11. Enforcement timeliness | If our enforcement activity is delayed, then we will be unable to deliver our core duty to prosecute within time limitations | 16 | 8 | 12 | Exceeds Tolerance
Op13. Learning from Patient Safety Events (LfPSE) | If we do not have an effective process for reviewing reported patient safety events for NHS Trusts that equate to statutory notification requirements, then this can cause a delay in handling individual specific incidents and missed regulatory risk. | 16 | 8 | 12 | Exceeds Tolerance
Reg1. Assessment Framework | If our Assessment Framework does not support our colleagues to deliver effective regulation, then we may be unable to ensure everyone receives safe, effective and compassionate care. | 15 | 8 | 12 | Exceeds Tolerance

## Slide 10: Corporate Risk
Reference | Risk | Risk Score | Appetite | Tolerance | Risk Status
Data and Information |  |  |  |  | 
DI1. Data quality | If our regulatory data is not of sufficient quality, then we will be unable to support and inform effective judgements and secondary analysis | 16 | 8 | 12 | Exceeds Tolerance
Sec3. Use of dual systems | If we continue to maintain HSCA Legal Register data on primarily Siebel CRM (new registrations, variations etc), but also Reg Platform (Cancellations, Enforcement condition changes etc) then data may become out of sync between the two systems and the register be inaccurate. | 16 | 8 | 12 | Exceeds Tolerance
People |  |  |  |  | 
P1a. Leadership structures | If we have gaps in our structures and leadership, then we will not effectively deliver our objectives | 15 | 10 | 15 | Exceeds Appetite
P1b. Leadership culture | If CQC leadership culture and behaviours do not align with the CQC Way, then we will not rebuild trust with colleagues | 20 | 10 | 15 | Exceeds Tolerance
P5. Staff morale and wellbeing following transition | If staff wellbeing and morale remains low following changes to ways of working, then this will negatively impact our productivity and culture | 20 | 10 | 15 | Exceeds Tolerance
P11 Training and guidance | If operational guidance and training to colleagues on the Assessment Framework and Regulatory Platform does not support colleagues, then we will not deliver core services effectively and impact on our credibility | 16 | 8 | 12 | Exceeds Tolerance
Op14 Operations capacity and capability | If we do not have the right number of people in roles with the right skills within Operations, then we will be unable to deliver our core services | 16 | 8 | 12 | Exceeds Tolerance
Programmes and Projects |  |  |  |  | 
PPB1. Programme budget | If the programme is already operating in deficit before formal budget approval, then the scope of the programme may be reduced and objectives not achieved. | 20 | 10 | 15 | Exceeds Tolerance
PPB2. Programme resource | If the programme does not have access to dedicated project resources (business change, project/delivery managers, business analysts) with the right combination of delivery expertise and organisational knowledge, then it will be unable to deliver its key projects to time, quality, or cost | 16 | 10 | 15 | Exceeds Tolerance
PPB3. Capacity to change | If we do not have the capacity to make changes, then the programme will face significant risks related to delivery capability and culture. | 20 | 10 | 15 | Exceeds Tolerance

## Slide 11: Corporate Risk
Reference | Risk | Risk Score | Appetite | Tolerance | Risk Status
Policy and Strategy |  |  |  |  | 
Reg4. S46 | If we are unable to deliver certainty for the frequency of assessments under section 46 of the Health and Social Care act 2008, then we will not meet our duties as a regulator | 16 | 10 | 15 | Exceeds Tolerance
Security |  |  |  |  | 
Sec2. Use of legacy systems | If we continue to operate legacy systems, then there is a risk of catastrophic failure and the integrity, confidentiality and availability of data may be compromised preventing delivery of our regulatory operational activity | 15 | 8 | 12 | Exceeds Tolerance
TDI1. Information governance compliance | If we are not compliant with information governance and records management policies, including failure to apply retention schedules, manage records effectively, and ensure secure data handling, then this could lead to data breaches | 16 | 8 | 12 | Exceeds Tolerance
Governance |  |  |  |  | 
G1. Governance arrangements | If we have unclear Board and Executive governance arrangements, then our decision making may be ineffective | 16 | 10 | 15 | Exceeds Tolerance
Stakeholder Management |  |  |  |  | 
Reg3. Stakeholder confidence in our ability to improve | If our stakeholders do not trust our planned approaches and abilities to improve our activity, then they may lose confidence in CQC as an effective regulator. | 20 | 8 | 12 | Exceeds Tolerance